## Report
FLOOR | AREA | Ceiling Gypsum / Box |  |  |  | Ceiling finishing - Painting / laminate / Wooden |  |  |  | Doors |  |  |  | Flooring |  |  |  | Furniture Built-in |  |  |  | Glass Wall |  |  |  | Skirting aluminium |  |  |  | Wall finishing - Laminate / Painting / Ceramic tile / Glass |  |  |  | Progress By Room | Completion date by room
|  | Start | finish | Progress | Material | Start | finish | Progress | Material | Start | finish | Progress | Material | Start | finish | Progress | Material | Start | finish | Progress | Material | Start | finish | Progress | Material | Start | finish | Progress | Material | Start | finish | Progress | Material
24TH FLOOR | AC |  |  | 100% |  | 23/04/2026 | 24/04/2026 | 50% | 100% | 28/04/2026 | 29/04/2026 |  | 50% |  |  | 100% | [5 empty] | 27/04/2026 | 29/04/2026 |  | 50% | 25/04/2026 | 25/04/2026 |  |  | 22/04/2026 | 24/04/2026 | 75% | 100% | 41% | 24/04/2026
| AC. SVR 01 |  |  | 100% |  | 25/04/2026 | 26/04/2026 | 50% | 100% | 28/04/2026 | 29/04/2026 |  | 50% |  |  | 100% | [5 empty] | 26/04/2026 | 28/04/2026 |  | 50% | 24/04/2026 | 24/04/2026 |  |  | 25/04/2026 | 26/04/2026 | 75% | 100% | 41% | 26/04/2026
| AC. SVR 02 |  |  | 100% |  | 25/04/2026 | 26/04/2026 | 50% | 100% | 28/04/2026 | 29/04/2026 |  | 50% |  |  | 100% | [5 empty] | 26/04/2026 | 28/04/2026 |  | 50% | 24/04/2026 | 24/04/2026 |  |  | 25/04/2026 | 26/04/2026 | 75% | 100% | 41% | 26/04/2026
| AC. SVR 03 |  |  | 100% |  | 23/04/2026 | 24/04/2026 | 50% | 100% | 28/04/2026 | 29/04/2026 |  | 50% |  |  | 100% | [5 empty] | 26/04/2026 | 28/04/2026 |  | 50% | 24/04/2026 | 24/04/2026 |  |  | 22/04/2026 | 24/04/2026 | 75% | 100% | 41% | 24/04/2026
| AC. SWT 01 |  |  | 100% |  | 25/04/2026 | 26/04/2026 | 50% | 100% | 27/04/2026 | 28/04/2026 | 25% | 75% |  |  | 100% | [5 empty] | 26/04/2026 | 28/04/2026 | 25% | 75% | 24/04/2026 | 24/04/2026 |  |  | 25/04/2026 | 26/04/2026 | 75% | 100% | 47% | 26/04/2026
| AC. SWT 02 |  |  | 100% |  | 25/04/2026 | 26/04/2026 | 50% | 100% | 27/04/2026 | 28/04/2026 | 25% | 75% |  |  | 100% | [5 empty] | 26/04/2026 | 28/04/2026 | 25% | 75% | 24/04/2026 | 24/04/2026 |  |  | 25/04/2026 | 26/04/2026 | 75% | 100% | 47% | 26/04/2026
| AC. SWT 03 |  |  | 100% |  | 25/04/2026 | 26/04/2026 | 50% | 100% | 27/04/2026 | 28/04/2026 | 25% | 75% |  |  | 100% | [5 empty] | 26/04/2026 | 28/04/2026 | 25% | 75% | 24/04/2026 | 24/04/2026 |  |  | 25/04/2026 | 26/04/2026 | 75% | 100% | 47% | 26/04/2026
| AC. SWT 04 |  |  | 100% |  | 25/04/2026 | 26/04/2026 | 50% | 100% | 27/04/2026 | 28/04/2026 | 25% | 75% |  |  | 100% | [5 empty] | 26/04/2026 | 28/04/2026 | 25% | 75% | 24/04/2026 | 24/04/2026 |  |  | 25/04/2026 | 26/04/2026 | 75% | 100% | 47% | 26/04/2026
| AC. SWT 05 |  |  | 100% |  | 25/04/2026 | 26/04/2026 | 50% | 100% | 27/04/2026 | 28/04/2026 | 25% | 75% |  |  | 100% | [5 empty] | 26/04/2026 | 28/04/2026 | 25% | 75% | 24/04/2026 | 24/04/2026 |  |  | 25/04/2026 | 26/04/2026 | 75% | 100% | 47% | 26/04/2026
| AC. SWT 06 |  |  | 100% |  | 25/04/2026 | 26/04/2026 | 50% | 100% | 27/04/2026 | 28/04/2026 |  | 50% |  |  | 100% | [5 empty] | 26/04/2026 | 28/04/2026 |  | 50% | 24/04/2026 | 24/04/2026 |  |  | 25/04/2026 | 26/04/2026 | 75% | 100% | 41% | 26/04/2026
| AM. SVR 04 |  |  | 100% |  | 23/04/2026 | 24/04/2026 | 50% | 100% | 28/04/2026 | 29/04/2026 |  | 50% |  |  | 100% | [5 empty] | 27/04/2026 | 29/04/2026 |  | 50% | 25/04/2026 | 25/04/2026 |  |  | 22/04/2026 | 24/04/2026 | 75% | 100% | 41% | 24/04/2026
| AM. SVR 06 |  |  | 100% |  | 23/04/2026 | 24/04/2026 | 50% | 100% | 28/04/2026 | 29/04/2026 |  | 50% |  |  | 100% | [5 empty] | 27/04/2026 | 29/04/2026 |  | 50% | 25/04/2026 | 25/04/2026 |  |  | 22/04/2026 | 24/04/2026 | 75% | 100% | 41% | 24/04/2026
| Assistant Manager |  |  | 100% |  | 25/04/2026 | 26/04/2026 | 50% | 100% | 27/04/2026 | 28/04/2026 |  | 50% |  |  | 100% | [5 empty] | 26/04/2026 | 28/04/2026 |  | 50% | 24/04/2026 | 24/04/2026 |  |  | 25/04/2026 | 26/04/2026 | 75% | 100% | 41% | 26/04/2026
| Construction |  |  | 100% |  |  |  | 100% |  | 26/04/2026 | 27/04/2026 | 25% | 75% |  |  | 100% |  | 25/04/2026 | 25/04/2026 | 75% |  | 25/04/2026 | 27/04/2026 | 25% | 75% | 23/04/2026 | 23/04/2026 |  |  | 27/04/2026 | 27/04/2026 | 75% | 100% | 63% | 27/04/2026
| Corridor |  |  | 100% |  | 29/04/2026 | 30/04/2026 | 50% | 100% | 29/04/2026 | 30/04/2026 |  | 50% | 29/04/2026 | 30/04/2026 | 75% | 100% |  |  |  |  | 27/04/2026 | 29/04/2026 |  | 50% | 26/04/2026 | 26/04/2026 |  |  | 27/04/2026 | 29/04/2026 | 75% | 100% | 38% | 30/04/2026
| Export Team |  |  | 100% |  |  |  | 100% | [7 empty] | 100% | [9 empty] | 23/04/2026 | 23/04/2026 |  |  | 27/04/2026 | 27/04/2026 | 75% | 100% | 47% | 23/04/2026
| General Manager |  |  | 100% |  | 25/04/2026 | 26/04/2026 | 50% | 100% | 27/04/2026 | 28/04/2026 |  | 50% |  |  | 100% |  | 27/04/2026 | 30/04/2026 | 25% |  | 26/04/2026 | 28/04/2026 |  | 50% | 24/04/2026 | 24/04/2026 |  |  | 25/04/2026 | 26/04/2026 | 75% | 100% | 44% | 26/04/2026
| Global Account |  |  | 100% |  | 23/04/2026 | 24/04/2026 | 50% | 100% | 28/04/2026 | 29/04/2026 |  | 50% |  |  | 100% |  | 25/04/2026 | 25/04/2026 | 75% |  | 27/04/2026 | 29/04/2026 |  | 50% | 25/04/2026 | 25/04/2026 |  |  | 22/04/2026 | 24/04/2026 | 75% | 100% | 50% | 24/04/2026
| Hubs Room |  |  | 100% |  | 25/04/2026 | 26/04/2026 | 50% | 100% | 27/04/2026 | 28/04/2026 |  | 50% |  |  | 100% | [5 empty] | 25/04/2026 | 27/04/2026 |  | 50% |  |  | 100% |  | 29/04/2026 | 30/04/2026 | 75% | 100% | 53% | 26/04/2026
| IT 4 pax. |  |  | 100% |  |  |  | 100% |  | 26/04/2026 | 27/04/2026 | 25% | 75% |  |  | 100% | [5 empty] | 25/04/2026 | 27/04/2026 | 25% | 75% | 23/04/2026 | 23/04/2026 |  |  | 27/04/2026 | 27/04/2026 | 75% | 100% | 53% | 27/04/2026
| Janitor | 24/04/2026 | 24/04/2026 |  | 100% | 29/04/2026 | 29/04/2026 |  | 100% | 29/04/2026 | 30/04/2026 |  | 50% | 22/04/2026 | 23/04/2026 | 25% | 100% |  |  |  |  | 27/04/2026 | 29/04/2026 |  | 50% | 30/04/2026 | 30/04/2026 |  |  | 28/04/2026 | 30/04/2026 |  | 100% | 3% | 24/04/2026
| Library |  |  | 100% |  |  |  | 100% |  | 26/04/2026 | 27/04/2026 | 25% | 75% |  |  | 100% | [5 empty] | 25/04/2026 | 27/04/2026 | 25% | 75% | 23/04/2026 | 23/04/2026 |  |  | 28/04/2026 | 29/04/2026 | 75% | 100% | 53% | 27/04/2026
| Lift Lobby | 26/04/2026 | 26/04/2026 | 80% | 100% | 29/04/2026 | 30/04/2026 | 25% | 100% | 29/04/2026 | 30/04/2026 |  | 50% | 25/04/2026 | 26/04/2026 | 50% | 100% |  |  |  |  | 27/04/2026 | 29/04/2026 |  | 50% | 29/04/2026 | 30/04/2026 |  |  | 24/04/2026 | 28/04/2026 | 25% | 100% | 23% | 26/04/2026
| Meeting room 10 seats |  |  | 100% |  | 25/04/2026 | 26/04/2026 | 50% | 100% | 28/04/2026 | 29/04/2026 |  | 50% |  |  | 100% | [5 empty] | 26/04/2026 | 28/04/2026 |  | 50% | 30/04/2026 | 30/04/2026 |  |  | 25/04/2026 | 26/04/2026 | 75% | 100% | 41% | 26/04/2026
| Prayer Room | 24/04/2026 | 24/04/2026 |  | 100% | 29/04/2026 | 29/04/2026 |  | 100% | 29/04/2026 | 30/04/2026 |  | 50% | 22/04/2026 | 23/04/2026 | 25% | 100% |  |  |  |  | 27/04/2026 | 29/04/2026 |  | 50% | 30/04/2026 | 30/04/2026 |  |  | 28/04/2026 | 30/04/2026 |  | 100% | 3% | 24/04/2026
| QA / Regulation |  |  | 100% |  |  |  | 100% | [7 empty] | 100% | [9 empty] | 23/04/2026 | 23/04/2026 |  |  | 27/04/2026 | 27/04/2026 | 75% | 100% | 47% | 23/04/2026
| SH 4 pax. |  |  | 100% |  |  |  | 100% |  | 26/04/2026 | 27/04/2026 | 25% | 75% |  |  | 100% | [5 empty] | 25/04/2026 | 27/04/2026 | 25% | 75% | 23/04/2026 | 23/04/2026 | 50% |  | 28/04/2026 | 29/04/2026 | 75% | 100% | 59% | 27/04/2026
| Sales Assistant |  |  | 100% |  | 23/04/2026 | 24/04/2026 | 50% | 100% | 29/04/2026 | 30/04/2026 |  | 50% |  |  | 100% |  | 27/04/2026 | 30/04/2026 | 25% |  | 27/04/2026 | 29/04/2026 |  | 50% | 25/04/2026 | 25/04/2026 |  |  | 22/04/2026 | 24/04/2026 | 75% | 100% | 44% | 24/04/2026
| Sales Manager SVR |  |  | 100% |  | 23/04/2026 | 24/04/2026 | 50% | 100% | 28/04/2026 | 29/04/2026 |  | 50% |  |  | 100% |  | 25/04/2026 | 25/04/2026 | 75% |  | 27/04/2026 | 29/04/2026 |  | 50% | 25/04/2026 | 25/04/2026 |  |  | 22/04/2026 | 24/04/2026 | 75% | 100% | 50% | 24/04/2026
| Sales Manager SWT |  |  | 100% |  | 23/04/2026 | 24/04/2026 | 50% | 100% | 28/04/2026 | 29/04/2026 |  | 50% |  |  | 100% |  | 25/04/2026 | 25/04/2026 | 75% |  | 27/04/2026 | 29/04/2026 |  | 50% | 25/04/2026 | 25/04/2026 |  |  | 22/04/2026 | 24/04/2026 | 75% | 100% | 50% | 24/04/2026
| Spare Office |  |  | 100% |  |  |  | 100% |  | 27/04/2026 | 28/04/2026 | 25% | 75% |  |  | 100% | [5 empty] | 25/04/2026 | 27/04/2026 | 25% | 75% | 23/04/2026 | 23/04/2026 |  |  | 27/04/2026 | 27/04/2026 | 75% | 100% | 53% | 28/04/2026
| Stair case | 25/04/2026 | 27/04/2026 |  | 100% | 29/04/2026 | 29/04/2026 |  | 100% | 29/04/2026 | 30/04/2026 |  | 50% | 24/04/2026 | 24/04/2026 | 75% | 100% |  |  |  |  | 29/04/2026 | 29/04/2026 |  | 50% | 30/04/2026 | 30/04/2026 |  |  | 29/04/2026 | 30/04/2026 |  | 100% | 9% | 27/04/2026
| Storage |  |  | 100% |  |  |  | 100% | [7 empty] | 100% |  | 24/04/2026 | 26/04/2026 | 25% | [5 empty] | 23/04/2026 | 23/04/2026 |  |  | 27/04/2026 | 27/04/2026 | 75% | 100% | 50% | 26/04/2026
TOTAL OF FLOOR | 33 Zones | 24/04/2026 | 24/04/2026 | 90% | 12% | 23/04/2026 | 24/04/2026 | 57% | 76% | 28/04/2026 | 29/04/2026 | 8% | 53% | 29/04/2026 | 30/04/2026 | 92% | 15% | 25/04/2026 | 25/04/2026 | 11% | 0% | 27/04/2026 | 29/04/2026 | 8% | 53% | 25/04/2026 | 25/04/2026 | 5% | 0% | 22/04/2026 | 24/04/2026 | 67% | 100% | 42% | 24/04/2026
25TH FLOOR | Assistants |  |  | 100% |  | 27/04/2026 | 29/04/2026 | 75% | 100% | 26/04/2026 | 29/04/2026 | 25% | 50% |  |  | 100% | [7 empty] | 50% | 50% | 27/04/2026 | 30/04/2026 | 50% | 100% | 26/04/2026 | 28/04/2026 | 75% | 100% | 59% | 29/04/2026
| BE.m Category |  |  | 100% |  | 27/04/2026 | 29/04/2026 | 75% | 100% | 26/04/2026 | 29/04/2026 | 50% |  |  |  | 100% |  | 25/04/2026 | 27/04/2026 | 75% | 100% |  |  | 25% | 50% | 27/04/2026 | 30/04/2026 | 50% | 100% | 26/04/2026 | 28/04/2026 | 50% | 100% | 66% | 29/04/2026
| Board Meeting Room |  |  | 100% |  | 27/04/2026 | 29/04/2026 | 75% | 100% | 26/04/2026 | 29/04/2026 | 50% | 50% |  |  | 100% |  | 25/04/2026 | 27/04/2026 | 80% | 100% |  |  | 50% | 50% | 27/04/2026 | 30/04/2026 |  |  | 25/04/2026 | 29/04/2026 | 50% | 100% | 63% | 29/04/2026
| CAT. DIR. ASS | 25/04/2026 | 30/04/2026 | 75% | 100% | 30/04/2026 | 02/05/2026 | 50% | 100% |  |  |  |  | 27/04/2026 | 29/04/2026 | 75% | 100% | 25/04/2026 | 27/04/2026 | 50% | 100% |  |  |  |  | 27/04/2026 | 30/04/2026 |  |  | 25/04/2026 | 29/04/2026 | 75% | 100% | 41% | 30/04/2026
| CAT. Division Director SAV. | 25/04/2026 | 30/04/2026 | 60% |  | 25/04/2026 | 27/04/2026 | 80% | 100% | 26/04/2026 | 29/04/2026 | 25% | 50% |  |  | 100% |  | 25/04/2026 | 27/04/2026 | 75% | 100% |  |  | 75% | 50% | 27/04/2026 | 30/04/2026 |  |  | 25/04/2026 | 29/04/2026 | 75% | 100% | 61% | 30/04/2026
| CAT. Division Director SWT. | 25/04/2026 | 30/04/2026 | 60% |  | 25/04/2026 | 30/04/2026 | 80% | 100% | 26/04/2026 | 29/04/2026 | 25% | 50% |  |  | 100% |  | 25/04/2026 | 27/04/2026 | 75% | 100% |  |  | 100% | 100% | 27/04/2026 | 30/04/2026 |  |  | 25/04/2026 | 29/04/2026 | 75% | 100% | 64% | 30/04/2026
| CI Room | 25/04/2026 | 30/04/2026 | 75% | 100% | 27/04/2026 | 29/04/2026 | 75% |  | 26/04/2026 | 29/04/2026 |  | 50% | 27/04/2026 | 29/04/2026 | 75% | 100% | 25/04/2026 | 28/04/2026 | 25% | 100% |  |  |  |  | 27/04/2026 | 30/04/2026 |  |  | 25/04/2026 | 29/04/2026 | 75% | 100% | 41% | 30/04/2026
| Corridor |  |  | 100% |  | 30/04/2026 | 02/05/2026 | 75% | [5 empty] | 27/04/2026 | 30/04/2026 | 75% | 100% |  |  |  | 100% |  |  |  |  | 27/04/2026 | 30/04/2026 |  |  | 28/04/2026 | 29/04/2026 | 50% | 100% | 38% | 02/05/2026
| Dairy Category Manager |  |  | 100% |  | 30/04/2026 | 02/05/2026 | 75% | 100% | 26/04/2026 | 29/04/2026 | 50% | 50% |  |  | 100% |  | 25/04/2026 | 27/04/2026 | 75% | 100% |  |  | 75% | 100% | 27/04/2026 | 30/04/2026 |  |  | 25/04/2026 | 26/04/2026 | 75% | 100% | 69% | 02/05/2026
| Ideation Space |  |  | 100% |  |  |  | 100% |  | 26/04/2026 | 29/04/2026 |  | 50% | 27/04/2026 | 28/04/2026 | 75% | 100% | 25/04/2026 | 28/04/2026 | 70% | 50% |  |  | 70% | 50% | 27/04/2026 | 30/04/2026 |  |  | 25/04/2026 | 26/04/2026 | 50% | 50% | 58% | 29/04/2026
| Janitor room |  |  | 100% |  |  |  | 100% |  | 26/04/2026 | 29/04/2026 | 25% | 50% |  |  | 100% | [15 empty] | 100% |  | 53% | 29/04/2026
| Lift lobby | 25/04/2026 | 30/04/2026 | 80% | 100% | 02/05/2026 | 04/05/2026 | 75% | 100% |  |  |  | 100% | 27/04/2026 | 30/04/2026 | 75% | 100% | [6 empty] | 25% | 100% | [7 empty] | 100% | 32% | 30/04/2026
| Market Manager + Team Leader & Assistant |  |  | 100% |  | 05/05/2026 | 06/05/2026 | 75% |  | 26/04/2026 | 29/04/2026 | 75% | 50% |  |  | 100% |  | 25/04/2026 | 28/04/2026 | 50% | 100% |  |  | 75% | 50% | 27/04/2026 | 30/04/2026 |  |  | 25/04/2026 | 29/04/2026 | 75% | 100% | 69% | 06/05/2026
| Meeting room |  |  | 100% |  | 05/05/2026 | 06/05/2026 | 75% |  | 26/04/2026 | 29/04/2026 |  |  |  |  | 100% | [9 empty] | 27/04/2026 | 30/04/2026 |  |  | 23/04/2026 | 27/04/2026 | 50% | 100% | 41% | 06/05/2026
| Observation Room |  |  | 100% |  | 05/05/2026 | 06/05/2026 | 75% | 100% | 26/04/2026 | 29/04/2026 | 25% |  | 28/04/2026 | 29/04/2026 | 60% | 100% | [8 empty] | 27/04/2026 | 30/04/2026 |  |  | 25/04/2026 | 29/04/2026 | 50% | 100% | 39% | 06/05/2026
| Open Space | 25/04/2026 | 30/04/2026 | 75% |  | 05/05/2026 | 06/05/2026 | 75% | [5 empty] | 27/04/2026 | 29/04/2026 | 75% | 100% | 02/05/2026 | 04/05/2026 | 50% | 50% |  |  |  |  | 27/04/2026 | 30/04/2026 |  |  | 25/04/2026 | 29/04/2026 | 75% | 100% | 44% | 30/04/2026
| Phone Booth | 25/04/2026 | 30/04/2026 | 50% | 100% | 25/04/2026 | 28/04/2026 | 75% | 100% | 26/04/2026 | 29/04/2026 | 25% | 50% | 29/04/2026 | 30/04/2026 | 60% | 75% | 25/04/2026 | 30/04/2026 | 50% | 50% |  |  | 50% | 100% | 27/04/2026 | 30/04/2026 |  |  |  |  | 25% |  | 42% | 30/04/2026
| SCI Manager | 23/04/2026 | 25/04/2026 | 50% | 100% | 25/04/2026 | 28/04/2026 |  | 100% | 26/04/2026 | 29/04/2026 |  | 100% |  |  | 100% |  | 25/04/2026 | 28/04/2026 | 75% | 100% |  |  |  | 100% | 27/04/2026 | 30/04/2026 |  |  | 25/04/2026 | 26/04/2026 | 50% | 100% | 34% | 25/04/2026
| Sansory Application Lab | 23/04/2026 | 25/04/2026 | 50% | 100% | 25/04/2026 | 28/04/2026 | 90% | 100% | 26/04/2026 | 29/04/2026 | 75% | 50% | 27/04/2026 | 29/04/2026 | 75% | 100% | [8 empty] | 27/04/2026 | 30/04/2026 |  |  | 25/04/2026 | 29/04/2026 | 25% | 100% | 39% | 25/04/2026
| Sever Room |  |  | 100% |  | 07/05/2026 | 07/05/2026 | 75% |  | 26/04/2026 | 29/04/2026 |  |  |  |  | 100% | [11 empty] | 100% |  | 25/04/2026 | 26/04/2026 |  | 100% | 47% | 07/05/2026
| Spare Office |  |  | 100% |  |  |  | 100% |  | 26/04/2026 | 29/04/2026 | 50% | 50% |  |  | 100% |  | 25/04/2026 | 27/04/2026 | 75% | 100% |  |  | 50% | 50% | 27/04/2026 | 30/04/2026 | 50% |  | 25/04/2026 | 27/04/2026 | 75% | 100% | 75% | 29/04/2026
| Stair case | 27/04/2026 | 30/04/2026 | 50% | 100% | 04/05/2026 | 05/05/2026 | 70% | 100% | 01/05/2026 | 03/05/2026 |  |  | 27/04/2026 | 28/04/2026 | 75% | 100% | [8 empty] | 27/04/2026 | 30/04/2026 |  |  |  |  | 50% | 100% | 31% | 30/04/2026
| Storage |  |  | 100% |  | 02/05/2026 | 02/05/2026 | 75% | 100% | 26/04/2026 | 29/04/2026 | 25% | 50% | 27/04/2026 | 28/04/2026 | 75% | 100% | [8 empty] | 27/04/2026 | 30/04/2026 |  |  | 25/04/2026 | 29/04/2026 | 75% | 100% | 44% | 02/05/2026
| Testing Room | 27/04/2026 | 30/04/2026 | 50% | 100% |  |  | 100% |  | 26/04/2026 | 29/04/2026 | 25% | 50% |  |  | 100% |  |  |  | 70% | 100% |  |  |  |  | 27/04/2026 | 30/04/2026 |  |  | 25/04/2026 | 29/04/2026 | 100% | 100% | 56% | 30/04/2026
| Toilet room Female |  |  | 100% |  | 28/05/2026 | 29/05/2026 | 75% |  | 26/04/2026 | 29/04/2026 | 50% | 50% |  |  | 100% | [17 empty] | 41% | 29/05/2026
| Toilet room Male |  |  | 100% |  | 28/05/2026 | 29/05/2026 | 75% |  | 26/04/2026 | 29/04/2026 | 50% | 50% |  |  | 100% | [17 empty] | 41% | 29/05/2026
TOTAL OF FLOOR | 26 Zones | 25/04/2026 | 30/04/2026 | 84% | 31% | 27/04/2026 | 29/04/2026 | 76% | 54% | 26/04/2026 | 29/04/2026 | 25% | 38% | 27/04/2026 | 29/04/2026 | 88% | 41% | 25/04/2026 | 27/04/2026 | 34% | 52% |  |  | 25% | 33% | 27/04/2026 | 30/04/2026 | 10% | 8% | 26/04/2026 | 28/04/2026 | 54% | 83% | 50% | 29/04/2026
26TH FLOOR | Air Lock (Corridor) | 2026-05-05 | 2026-05-06 | 80% |  | 2026-05-07 | 2026-05-07 | 75% | 100% | 2026-05-10 | 2026-05-13 | 75% | 100% | 2026-05-06 | 2026-05-06 | 75% | [5 empty] | 2026-05-09 | 2026-05-09 | 90% | 100% | 2026-05-08 | 2026-05-08 |  |  | 2026-05-05 | 2026-05-06 | 50% |  | 56% | 2026-05-13
| Air Lock (Smelly Lab) | 2026-05-05 | 2026-05-06 | 80% |  | 2026-05-07 | 2026-05-07 | 75% | 100% | 2026-05-10 | 2026-05-13 | 75% | 100% | 2026-05-06 | 2026-05-06 | 75% | [5 empty] | 2026-05-09 | 2026-05-09 | 90% | 100% | 2026-05-08 | 2026-05-08 |  |  | 2026-05-05 | 2026-05-06 | 50% |  | 56% | 2026-05-13
| Analytical Lab | 2026-05-05 | 2026-05-06 | 90% |  | 2026-05-07 | 2026-05-07 | 85% | 100% | 2026-05-10 | 2026-05-13 | 75% | 50% | 2026-02-06 | 2026-02-06 | 80% | [5 empty] | 2026-05-09 | 2026-05-09 | 90% | 50% | 2026-05-08 | 2026-05-08 |  |  | 2026-05-05 | 2026-05-06 | 70% | 100% | 61% | 2026-05-13
| Analytical Office | 2026-06-05 | 2026-06-06 | 80% |  | 2026-05-07 | 2026-05-07 | 80% |  | 2026-05-10 | 2026-05-13 | 75% | 100% | 2026-05-09 | 2026-05-09 | 90% | [5 empty] | 2026-05-09 | 2026-05-09 | 90% | 100% | 2026-05-08 | 2026-05-08 |  |  | 2026-05-06 | 2026-05-06 | 85% | 100% | 63% | 2026-06-06
| Application Lab | 2026-05-04 | 2026-05-06 | 80% |  | 2026-05-05 | 2026-05-08 | 80% | 100% |  |  |  |  | 2026-05-04 | 2026-05-07 | 75% |  | 2026-05-05 | 2026-05-06 | 25% | [5 empty] | 2026-05-08 | 2026-05-09 |  |  | 2026-05-07 | 2026-05-08 | 80% | 100% | 43% | 2026-05-09
| Beverage Pilot |  |  | 85% | 100% |  |  | 100% | 100% | 23/04/2026 | 27/04/2026 | 25% | 100% | 24/04/2026 | 25/04/2026 | 75% | [5 empty] | 23/04/2026 | 27/04/2026 | 25% | 100% | 27/04/2026 | 27/04/2026 |  |  |  |  | 100% |  | 51% | 27/04/2026
| Buffer Stock Storage |  |  | 100% |  |  |  | 100% | 100% | 23/04/2026 | 27/04/2026 | 25% | 100% | 23/04/2026 | 24/04/2026 | 75% | [5 empty] | 23/04/2026 | 27/04/2026 | 25% | 100% | 26/04/2026 | 26/04/2026 |  |  |  |  | 100% |  | 53% | 27/04/2026
| Coffee & Alcohol bar |  |  | 100% |  |  |  | 100% |  | 28/04/2026 | 29/04/2026 |  | 50% | 24/04/2026 | 25/04/2026 | 75% | [5 empty] | 28/04/2026 | 29/04/2026 |  | 50% | 27/04/2026 | 27/04/2026 |  |  |  |  | 100% |  | 47% | 29/04/2026
| Collection Manager |  |  | 100% |  |  |  | 100% |  | 23/04/2026 | 27/04/2026 | 25% |  |  |  | 100% |  | 23/04/2026 | 23/04/2026 | 50% | 100% | 23/04/2026 | 27/04/2026 | 25% |  | 26/04/2026 | 26/04/2026 | 75% |  |  |  | 100% |  | 72% | 27/04/2026
| Compounding Main Lab |  |  | 100% |  | 25/04/2026 | 27/04/2026 | 80% | 100% | 23/04/2026 | 27/04/2026 | 25% | 100% | 23/04/2026 | 24/04/2026 | 80% | [5 empty] | 23/04/2026 | 27/04/2026 | 25% | 100% | 26/04/2026 | 26/04/2026 |  |  | 25/04/2026 | 26/04/2026 | 85% | 100% | 49% | 27/04/2026
| Conf & Bakery |  |  | 100% |  |  |  | 100% |  | 23/04/2026 | 27/04/2026 | 25% | 100% |  |  | 100% | [5 empty] | 23/04/2026 | 27/04/2026 | 25% | 100% | 27/04/2026 | 27/04/2026 |  |  | 25/04/2026 | 26/04/2026 | 85% | 100% | 54% | 27/04/2026
| Corridor | 25/04/2026 | 27/04/2026 | 80% | 100% | 21/04/2026 | 26/04/2026 | 75% | 100% | 23/04/2026 | 27/04/2026 | 25% | 100% | 25/04/2026 | 26/04/2026 | 75% | [5 empty] | 23/04/2026 | 27/04/2026 | 25% | 100% | 26/04/2026 | 27/04/2026 |  |  | 25/04/2026 | 26/04/2026 | 85% | 100% | 46% | 27/04/2026
| Creation Manager |  |  | 100% |  |  |  | 100% |  | 23/04/2026 | 27/04/2026 | 25% |  |  |  | 100% |  | 23/04/2026 | 23/04/2026 | 50% | 100% | 23/04/2026 | 27/04/2026 | 25% |  | 26/04/2026 | 26/04/2026 | 75% |  | 25/04/2026 | 26/04/2026 | 85% |  | 70% | 27/04/2026
| Evaluation Manager |  |  | 100% |  |  |  | 100% |  | 23/04/2026 | 27/04/2026 | 25% |  |  |  | 100% |  | 23/04/2026 | 23/04/2026 | 50% | 100% | 23/04/2026 | 27/04/2026 | 25% |  | 26/04/2026 | 26/04/2026 | 75% |  | 25/04/2026 | 26/04/2026 | 85% |  | 70% | 27/04/2026
| Flavorist Office 1 |  |  | 100% |  |  |  | 100% |  | 23/04/2026 | 27/04/2026 | 50% |  |  |  | 100% | [5 empty] | 23/04/2026 | 27/04/2026 | 50% |  | 26/04/2026 | 26/04/2026 | 75% |  |  |  | 100% |  | 72% | 27/04/2026
| Flavorist Office 2 |  |  | 100% |  |  |  | 100% |  | 23/04/2026 | 27/04/2026 | 50% |  |  |  | 100% | [5 empty] | 23/04/2026 | 27/04/2026 | 50% |  | 26/04/2026 | 26/04/2026 | 75% |  |  |  | 100% |  | 72% | 27/04/2026
| Flavorist Office 3 |  |  | 100% |  |  |  | 100% |  | 23/04/2026 | 27/04/2026 | 50% |  |  |  | 100% | [5 empty] | 23/04/2026 | 27/04/2026 | 50% |  | 26/04/2026 | 26/04/2026 | 75% |  |  |  | 100% |  | 72% | 27/04/2026
| Food Tech. | 24/04/2026 | 25/04/2026 | 95% | 100% | 24/04/2026 | 25/04/2026 | 90% | 100% | 23/04/2026 | 27/04/2026 |  | 100% | 25/04/2026 | 26/04/2026 | 80% |  | 24/04/2026 | 26/04/2026 | 25% | 100% | 23/04/2026 | 27/04/2026 |  | 100% | 27/04/2026 | 27/04/2026 |  |  | 23/04/2026 | 24/04/2026 | 50% | 100% | 43% | 25/04/2026
| Foyer |  |  | 100% |  | 23/04/2026 | 23/04/2026 | 80% | 100% |  |  |  |  | 25/04/2026 | 26/04/2026 | 90% | [9 empty] | 26/04/2026 | 26/04/2026 |  |  | 24/04/2026 | 25/04/2026 | 50% | 100% | 40% | 23/04/2026
| Gas Storage |  |  | 100% |  |  |  | 100% |  | 23/04/2026 | 27/04/2026 |  | 50% | 25/04/2026 | 26/04/2026 | 90% | [5 empty] | 23/04/2026 | 27/04/2026 |  | 50% | 26/04/2026 | 26/04/2026 |  |  | 25/04/2026 | 26/04/2026 | 85% |  | 47% | 27/04/2026
| Guest Office |  |  | 100% |  |  |  | 100% |  | 23/04/2026 | 27/04/2026 | 25% | 100% |  |  | 100% | [5 empty] | 23/04/2026 | 27/04/2026 | 25% | 100% | 26/04/2026 | 26/04/2026 | 75% |  |  |  | 100% |  | 66% | 27/04/2026
| IT Room |  |  | 100% |  | 25/04/2026 | 25/04/2026 | 90% | 100% | 23/04/2026 | 27/04/2026 |  | 50% |  |  | 100% | [5 empty] | 23/04/2026 | 27/04/2026 |  | 50% |  |  | 100% |  |  |  | 100% |  | 61% | 25/04/2026
| Informal Testing 1 |  |  | 100% |  | 25/04/2026 | 26/04/2026 | 75% | 100% | [6 empty] | 100% |  | 23/04/2026 | 23/04/2026 | 50% | 100% | [6 empty] | 100% |  | 26/04/2026 | 27/04/2026 | 90% |  | 64% | 26/04/2026
| Informal Testing 2 |  |  | 100% |  |  |  | 100% |  | 23/04/2026 | 27/04/2026 |  | 50% |  |  | 100% |  | 24/04/2026 | 24/04/2026 | 50% | 100% | 23/04/2026 | 27/04/2026 |  | 50% |  |  | 100% |  | 26/04/2026 | 27/04/2026 | 90% |  | 68% | 27/04/2026
| Junior Flavorist |  |  | 100% |  |  |  | 100% |  |  |  | 100% |  | 22/04/2026 | 23/04/2026 | 90% |  | 24/04/2026 | 26/04/2026 | 25% | 100% |  |  | 100% |  | 26/04/2026 | 26/04/2026 | 75% |  | 26/04/2026 | 27/04/2026 | 90% |  | 85% | 23/04/2026
| Large Meeting room |  |  | 100% |  | 21/04/2026 | 23/04/2026 | 90% | 100% | 23/04/2026 | 27/04/2026 | 50% | 50% |  |  | 100% |  | 24/04/2026 | 26/04/2026 | 25% | 100% | 23/04/2026 | 27/04/2026 | 50% | 50% | 27/04/2026 | 27/04/2026 |  |  | 25/04/2026 | 26/04/2026 | 80% | 100% | 62% | 23/04/2026
| Lift Lobby | 23/04/2026 | 27/04/2026 | 75% | 75% | 26/04/2026 | 28/04/2026 |  | 100% | 23/04/2026 | 27/04/2026 |  | 50% | 23/04/2026 | 24/04/2026 | 90% | [5 empty] | 23/04/2026 | 27/04/2026 |  | 50% | 27/04/2026 | 27/04/2026 |  |  | 25/04/2026 | 26/04/2026 | 50% | 100% | 27% | 27/04/2026
| Lockers |  |  | 100% |  |  |  | 100% | [5 empty] | 25/04/2026 | 26/04/2026 | 90% |  | 26/04/2026 | 26/04/2026 | 50% | 100% |  |  |  |  | 27/04/2026 | 27/04/2026 |  |  |  |  | 100% |  | 55% | 26/04/2026
| Logistic & Library |  |  | 100% |  | 25/04/2026 | 25/04/2026 | 90% | 100% | 23/04/2026 | 27/04/2026 | 50% | 50% | 23/04/2026 | 24/04/2026 | 90% | [5 empty] | 23/04/2026 | 27/04/2026 | 50% | 50% | 26/04/2026 | 26/04/2026 |  |  | 24/04/2026 | 25/04/2026 | 50% | 100% | 54% | 25/04/2026
| Meeting room |  |  | 100% |  | 25/04/2026 | 28/04/2026 | 90% | 100% | 23/04/2026 | 27/04/2026 | 25% | 50% |  |  | 100% |  | 24/04/2026 | 26/04/2026 | 25% | 100% | 23/04/2026 | 27/04/2026 | 25% | 50% | 27/04/2026 | 27/04/2026 |  |  | 25/04/2026 | 26/04/2026 | 50% | 100% | 52% | 28/04/2026
| PL Office area | 26/04/2026 | 27/04/2026 | 90% |  | 26/04/2026 | 27/04/2026 | 90% | 100% |  |  |  |  | 25/04/2026 | 26/04/2026 | 90% |  | 25/04/2026 | 25/04/2026 | 50% | 100% |  |  |  |  | 26/04/2026 | 26/04/2026 |  |  | 26/04/2026 | 27/04/2026 | 80% |  | 50% | 27/04/2026
| Phone Booth 1 |  |  | 100% |  |  |  | 100% |  | 23/04/2026 | 27/04/2026 | 25% | 50% |  |  | 100% |  | 24/04/2026 | 26/04/2026 | 25% | 100% | 23/04/2026 | 27/04/2026 | 25% | 50% | 27/04/2026 | 27/04/2026 | [6 empty] | 47% | 27/04/2026
| Phone POD |  |  | 100% |  |  |  | 100% |  | 23/04/2026 | 27/04/2026 |  | 50% |  |  | 100% |  | 24/04/2026 | 26/04/2026 | 25% | 100% | 23/04/2026 | 27/04/2026 |  | 50% | 27/04/2026 | 27/04/2026 | [6 empty] | 41% | 27/04/2026
| Printing Station |  |  | 100% |  |  |  | 100% | [7 empty] | 100% |  | 24/04/2026 | 26/04/2026 | 25% | 100% |  |  |  |  | 26/04/2026 | 26/04/2026 |  |  | 25/04/2026 | 26/04/2026 | 80% | 100% | 51% | 26/04/2026
| Smelly Lab (PMO) |  |  | 100% |  |  |  | 100% |  | 23/04/2026 | 27/04/2026 | 25% | 50% | 25/04/2026 | 26/04/2026 | 90% | [5 empty] | 23/04/2026 | 27/04/2026 | 25% | 50% | 26/04/2026 | 26/04/2026 |  |  |  |  | 100% |  | 55% | 27/04/2026
| Stair case | 21/04/2026 | 27/04/2026 | 25% | 50% | 21/04/2026 | 26/04/2026 | 25% | 50% | 23/04/2026 | 27/04/2026 |  | 50% | 26/04/2026 | 27/04/2026 | 90% | [5 empty] | 23/04/2026 | 27/04/2026 |  | 50% | 28/04/2026 | 28/04/2026 |  |  | 21/04/2026 | 27/04/2026 | 25% | 100% | 21% | 27/04/2026
| Storage |  |  | 100% |  |  |  | 100% |  | 23/04/2026 | 27/04/2026 |  | 50% |  |  | 100% | [5 empty] | 23/04/2026 | 27/04/2026 |  | 50% | 27/04/2026 | 27/04/2026 |  |  |  |  | 100% |  | 50% | 27/04/2026
| Strong Smell |  |  | 100% |  |  |  | 100% |  | 23/04/2026 | 27/04/2026 |  | 50% |  |  | 100% | [5 empty] | 23/04/2026 | 27/04/2026 |  | 50% | 27/04/2026 | 27/04/2026 |  |  |  |  | 100% |  | 50% | 27/04/2026
| Sweet Flavor Technical Director |  |  | 100% |  |  |  | 100% |  | 23/04/2026 | 27/04/2026 | 50% |  |  |  | 100% |  | 23/04/2026 | 23/04/2026 | 50% | 100% | 23/04/2026 | 27/04/2026 | 50% |  | 26/04/2026 | 26/04/2026 | 75% |  | 25/04/2026 | 26/04/2026 | 85% |  | 76% | 27/04/2026
| TCDC Assistant |  |  | 100% |  |  |  | 100% |  | 23/04/2026 | 27/04/2026 | 50% |  |  |  | 100% | [5 empty] | 23/04/2026 | 27/04/2026 | 50% |  | 26/04/2026 | 26/04/2026 | 75% |  |  |  | 100% |  | 72% | 27/04/2026
| Toilet room Female |  |  | 100% |  |  |  | 100% |  | 23/04/2026 | 27/04/2026 | 25% |  |  |  | 100% |  | 27/04/2026 | 27/04/2026 | 50% | 100% | 23/04/2026 | 27/04/2026 | 25% | [7 empty] | 100% |  | 63% | 27/04/2026
| Toilet room Male |  |  | 100% |  |  |  | 100% |  | 23/04/2026 | 27/04/2026 | 25% |  |  |  | 100% |  | 27/04/2026 | 27/04/2026 | 50% | 100% | 23/04/2026 | 27/04/2026 | 25% | [7 empty] | 100% |  | 63% | 27/04/2026
| Waste MGT |  |  | 100% |  |  |  | 100% |  | 23/04/2026 | 27/04/2026 | 25% | 50% | 25/04/2026 | 26/04/2026 | 90% | [5 empty] | 23/04/2026 | 27/04/2026 | 25% | 50% | 26/04/2026 | 26/04/2026 |  |  |  |  | 100% |  | 55% | 27/04/2026
TOTAL OF FLOOR | 43 Zones | 2026-05-04 | 2026-06-06 | 94% | 10% | 2026-05-05 | 2026-05-08 | 90% | 41% | 2026-05-10 | 2026-05-13 | 26% | 42% | 2026-02-06 | 2026-05-09 | 92% | 0% | 2026-05-05 | 2026-05-06 | 16% | 40% | 2026-05-09 | 2026-05-09 | 28% | 42% | 2026-05-08 | 2026-05-09 | 24% | 0% | 2026-05-05 | 2026-05-08 | 79% | 33% | 56% | 2026-06-06
27TH FLOOR | APPLICATION MANAGER |  |  | 100% |  |  |  | 100% |  | 2026-04-29 | 2026-04-29 | 25% | 100% |  |  | 100% |  |  |  | 100% |  |  |  | 100% |  |  |  | 100% |  | 29/04/2026 | 30/04/2026 | 60% | 100% | 86% | 2026-04-29
| BOOTH 01 |  |  | 100% |  | 02/05/2026 | 05/05/2026 | 75% | 100% | 27/04/2026 | 30/04/2026 |  |  |  |  | 100% | 100% | 06/05/2026 | 10/05/2026 |  |  | 27/04/2026 | 30/04/2026 | [10 empty] | 34% | 10/05/2026
| BOOTH 02 |  |  | 100% |  | 02/05/2026 | 05/05/2026 | 75% | 100% | 27/04/2026 | 30/04/2026 |  |  |  |  | 100% | 100% | 06/05/2026 | 10/05/2026 |  |  | 27/04/2026 | 30/04/2026 | [10 empty] | 34% | 10/05/2026
| COMPOUNDING FLAVOUR LAB | 03/05/2025 | 04/05/2026 | 70% | 100% | 05/05/2026 | 06/05/2026 | 60% | 100% | 28/04/2026 | 28/04/2026 | 25% | 100% | 05/05/2026 | 05/05/2026 | 90% | [7 empty] | 100% |  | 30/04/2026 | 30/04/2026 |  | 100% | 29/04/2026 | 30/04/2026 | 75% |  | 53% | 06/05/2026
| COMPOUNDING SEASONING LAB | 03/05/2025 | 04/05/2026 | 70% | 100% | 05/05/2026 | 06/05/2026 | 60% | 100% | 27/04/2026 | 28/04/2026 | 25% | 50% | 05/05/2026 | 05/05/2026 | 90% |  |  | 05/05/2026 |  |  |  |  | 100% |  | 29/04/2026 | 29/04/2026 |  | 100% | 28/04/2026 | 29/04/2026 | 75% |  | 53% | 06/05/2026
| CORRIDOR1 |  |  | 100% |  |  |  | 100% |  |  |  | 100% |  | 04/05/2026 | 05/05/2026 | 75% | 100% | [8 empty] | 07/05/2026 | 09/05/2026 |  | 100% | 01/05/2026 | 06/05/2026 |  |  | 47% | 09/05/2026
| CORRIDOR2 |  |  | 100% |  |  |  | 100% |  |  |  | 100% |  | 04/05/2026 | 05/05/2026 | 75% | 100% | [8 empty] | 07/05/2026 | 09/05/2026 |  | 100% | 01/05/2026 | 06/05/2026 |  |  | 47% | 09/05/2026
| CORRIDOR3 (Zone kitchen) | 30/04/2026 | 03/05/2026 | 80% | 100% | 04/05/2026 | 07/05/2026 | 80% | 100% | 03/05/2026 | 05/05/2026 | 25% |  | 04/05/2026 | 05/05/2026 | 75% | 100% |  |  |  |  | 03/05/2026 | 04/05/2026 | 60% |  | 07/05/2026 | 09/05/2026 |  | 100% | 01/05/2026 | 06/05/2026 | 60% | 100% | 48% | 09/05/2026
| CREATION FLAVOR MANAGER |  |  | 100% |  |  |  | 100% |  | 29/04/2026 | 29/04/2026 | 25% | 100% |  |  | 100% |  |  |  | 100% |  |  |  | 100% |  |  |  | 100% |  | 29/04/2026 | 30/04/2026 | 60% | 100% | 86% | 29/04/2026
| CREATION SEASONING MANAGER |  |  | 100% |  |  |  | 100% |  | 29/04/2026 | 29/04/2026 | 25% | 100% |  |  | 100% |  |  |  | 100% |  | 23/04/2026 | 23/04/2026 | 25% | 100% |  |  | 100% |  | 29/04/2026 | 30/04/2026 | 60% | 100% | 76% | 29/04/2026
| CULINARY LABS | 01/05/2026 | 05/05/2026 | 50% | 100% | 06/05/2026 | 07/05/2026 | 50% | 100% | 06/05/2026 | 07/05/2026 |  |  | 06/05/2026 | 06/05/2026 | 60% | 50% | [8 empty] | 07/05/2026 | 07/05/2026 |  | 100% |  |  |  |  | 20% | 07/05/2026
| DEMO KITCHEN | 26/04/2026 | 28/04/2026 | 90% | 100% | 23/04/2026 | 27/04/2026 | 60% | 100% | 29/04/2026 | 30/04/2026 | 25% | 100% | 29/04/2026 | 01/05/2026 | 60% | 60% | 24/04/2026 | 28/04/2026 | 25% | 25% | 29/04/2026 | 30/04/2026 | 75% | 100% | 02/05/2026 | 02/05/2026 |  | 100% | 25/04/2026 | 28/04/2026 | 60% | 50% | 49% | 28/04/2026
| EVALUATION ROOM |  |  | 100% |  |  |  | 100% | [7 empty] | 100% | [9 empty] | 28/04/2026 | 28/04/2026 |  |  | 24/04/2026 | 25/04/2026 | 75% |  | 47% | 28/04/2026
| FLAVORIST TASTING ROOOM |  |  | 100% |  |  |  | 100% |  | 27/04/2026 | 27/04/2026 | 75% | 100% |  |  | 100% | [7 empty] | 100% |  |  |  | 100% |  |  |  | 100% |  | 84% | 27/04/2026
| Flavorist Office |  |  | 100% |  |  |  | 100% | [7 empty] | 100% |  | 28/04/2026 | 30/04/2026 | 50% | 100% |  |  | 100% |  | 07/05/2026 | 09/05/2026 |  | 100% | 29/04/2026 | 30/04/2026 | 25% | 100% | 59% | 30/04/2026
| Guest Office |  |  | 100% |  |  |  | 100% | [7 empty] | 100% | [7 empty] | 100% |  | 01/05/2026 | 01/05/2026 |  | 100% | 28/04/2026 | 30/04/2026 | 50% | 100% | 56% | 01/05/2026
| IT ROOM |  |  | 100% |  |  |  | 100% |  | 29/04/2026 | 30/04/2026 |  | 100% |  |  | 100% | [11 empty] | 100% |  | 29/04/2026 | 30/04/2026 | 75% | 100% | 59% | 30/04/2026
| Janitor room |  |  | 100% | [5 empty] | 30/04/2026 | 30/04/2026 | 50% |  |  |  | 100% | [15 empty] | 100% |  | 44% | 30/04/2026
| LARGE MEETING ROOM | 28/04/2026 | 30/04/2026 | 75% | 100% |  |  | 75% | 100% | 28/04/2026 | 28/04/2026 | 25% | 100% |  |  | 100% |  | 29/04/2026 | 30/04/2026 | 75% | 100% | 01/04/2026 | 01/04/2026 | 75% |  |  |  | 100% |  | 30/04/2026 | 30/04/2026 | 75% | 100% | 75% | 30/04/2026
| LIBRARY & FLAVOUR STOCKS ROOM |  |  | 100% |  |  |  | 100% |  | 27/04/2026 | 27/04/2026 | 75% | 100% | 28/04/2026 | 284/2026 | 75% | [5 empty] | 22/04/2026 | 25/04/2026 | 25% | 100% |  |  | 100% |  | 23/04/2026 | 26/04/2026 | 60% |  | 67% | 27/04/2026
| LIFT LOBBY |  |  | 100% |  | 27/04/2026 | 27/04/2026 | 75% | 100% | 02/04/2026 | 02/04/2026 |  | 100% | 03/05/2026 | 03/05/2026 | 75% | 100% | [6 empty] | 100% |  | 01/05/2026 | 01/05/2026 |  | 100% | 27/04/2026 | 27/04/2026 | 50% | 100% | 50% | 27/04/2026
| LOCKERS CHANGING ROOM |  |  | 100% |  |  |  | 100% |  | 03/04/2026 | 03/04/2026 | 25% | 100% | 29/04/2026 | 29/04/2026 | 75% | 100% | 23/04/2026 | 27/04/2026 | 80% | 100% | 27/04/2026 | 27/04/2026 | 25% | 100% |  |  |  |  | 28/04/2026 | 28/04/2026 | 25% | 100% | 54% | 03/04/2026
| LOGISTIC ROOM |  |  | 100% |  |  |  | 100% |  | 27/04/2026 | 27/04/2026 |  | 100% | 25/04/2026 | 25/04/2026 | 50% | 100% | 24/04/2026 | 28/04/2026 | 50% | 100% |  |  | 100% | [5 empty] | 22/04/2026 | 24/04/2206 | 80% |  | 60% | 27/04/2026
| Logistic Storage |  |  | 100% |  |  |  | 100% |  | 22/04/2026 | 24/04/2026 | 25% | 100% | 27/04/2026 | 27/04/2026 | 75% | 100% | [6 empty] | 100% |  |  |  | 100% |  | 28/04/2026 | 28/04/2026 | 75% | 100% | 72% | 24/04/2026
| MEETING ROOM |  |  | 100% |  |  |  | 100% |  | 28/04/2026 | 28/04/2026 | 25% | 100% |  |  | 100% |  |  |  | 100% |  |  |  | 100% |  |  |  | 100% |  |  |  | 100% |  | 91% | 28/04/2026
| OPEN SPACE | 21/04/2026 | 30/04/2026 | 50% | 100% | 01/05/2026 | 05/05/2026 | 50% | [7 empty] | 100% | 100% | 01/05/2026 | 07/05/2026 | [14 empty] | 25% | 30/04/2026
| PILOT PLAN |  |  | 100% |  |  |  | 100% |  | 03/05/2026 | 05/04/2026 |  |  | 02/05/2026 | 04/05/2026 | 50% | 50% | [11 empty] | 100% |  |  |  |  | 31% | 05/04/2026
| PREPARATION STORAGE | 28/04/2026 | 30/04/2026 | 50% | 100% | 01/05/2026 | 02/05/2026 |  | 100% | 23/04/2026 | 24/04/2026 |  | 100% | 29/04/2026 | 29/04/2026 | 75% | 100% | [11 empty] | 100% |  |  |  |  | 16% | 30/04/2026
| PROFOR ROOM |  |  | 100% |  |  |  | 100% |  | 02/05/2026 | 02/05/2026 | 25% | 100% | 30/04/2026 | 30/04/2026 | 90% | [13 empty] | 29/04/2026 | 29/04/2026 | 75% | 100% | 49% | 02/05/2026
| SAVORY FLAVOR TECHNICADL DIRECTOR |  |  | 100% |  |  |  | 100% |  | 29/04/2026 | 29/04/2026 | 25% | 100% |  |  | 100% |  |  |  | 100% |  | 23/04/2026 | 23/04/2026 | 25% | 100% |  |  | 100% |  |  |  | 100% |  | 81% | 29/04/2026
| SEASONING TASTING ROOM |  |  | 100% |  |  |  | 100% |  | 27/04/2026 | 27/04/2026 | 75% | 100% |  |  | 100% | [7 empty] | 100% |  |  |  | 100% |  |  |  | 100% |  | 84% | 27/04/2026
| SMELLY LAB |  |  | 100% |  |  |  | 100% |  | 28/04/2026 | 28/04/2026 | 75% | 100% |  |  | 100% | 100% | [6 empty] | 100% |  | 01/04/2026 | 01/04/2026 |  | 100% |  |  | 100% |  | 72% | 28/04/2026
| SNACK APP |  |  | 100% |  |  |  | 100% |  | 28/04/2026 | 28/04/2026 | 75% | 100% |  |  | 100% | [5 empty] | 27/04/2026 | 28/04/2026 | 75% | 100% |  |  | 100% |  | 01/05/2026 | 02/05/2026 | 60% |  | 76% | 28/04/2026
| STAIRCASE | 28/04/2026 | 02/05/2026 |  | 100% | 03/05/2026 | 05/05/2026 |  | 100% | 03/05/2026 | 05/05/2026 |  |  | 30/04/2026 | 30/04/2026 | 75% | 100% |  |  | 75% |  | 03/05/2026 | 05/05/2026 |  |  | 01/05/2026 | 01/05/2026 |  |  | 01/05/2026 | 05/05/2026 |  |  | 19% | 05/05/2026
| Storage |  |  | 100% |  |  |  | 100% |  | 30/04/2026 | 30/04/2026 |  |  |  |  | 100% | [9 empty] | 03/05/2026 | 03/05/2026 |  | 100% | 28/04/2026 | 02/05/2026 | 100% |  | 50% | 30/04/2026
| TOILET FEMALE |  |  | 100% |  |  |  | 100% |  | 30/04/2026 | 30/04/2026 | 50% |  |  |  | 100% |  | 29/04/2026 | 30/04/2026 | 50% | [11 empty] | 100% |  | 63% | 30/04/2026
| TOILET MALE |  |  | 100% |  |  |  | 100% |  | 30/04/2026 | 30/04/2026 | 50% |  |  |  | 100% |  | 29/04/2026 | 30/04/2026 | 50% | [11 empty] | 100% |  | 63% | 30/04/2026
| Technologist & PL Office |  |  | 100% |  |  |  | 100% | [7 empty] | 100% |  | 28/04/2026 | 30/04/2026 | 50% | 100% |  |  | 100% |  | 07/05/2026 | 09/05/2026 |  | 100% | 29/04/2026 | 30/04/2026 | 25% | 100% | 59% | 30/04/2026
TOTAL OF FLOOR | 38 Zones | 03/05/2025 | 05/05/2026 | 90% | 24% | 01/05/2026 | 07/05/2026 | 83% | 29% | 02/04/2026 | 07/05/2026 | 28% | 54% | 02/05/2026 | 06/05/2026 | 89% | 38% | 01/05/2026 | 10/05/2026 | 26% | 14% | 27/04/2026 | 30/04/2026 | 47% | 16% | 30/04/2026 | 30/04/2026 | 32% | 39% | 29/04/2026 | 30/04/2026 | 55% | 36% | 56% | 10/05/2026